## Action Plans
Customer Satisfaction Improvement Action Plans
Initiative | Owner | Target Metric | Baseline | Goal | Timeline | Status
Improve First Contact Resolution | Michael Chen | FCR Rate | 75% | 85% | 90 days | In Progress
Reduce Resolution Time | Michael Chen | Avg Resolution | 3.4 hrs | 2 hrs | 120 days | In Progress
SMB Customer Program | Lisa Anderson | SMB Satisfaction | 4.0 | 4.2 | 180 days | Planned
Value Communication Initiative | Lisa Anderson | Value Score | 3.9 | 4.3 | 60 days | In Progress
Support Team Training | Michael Chen | Support Quality | 4.0 | 4.5 | 90 days | In Progress
Detailed Action Breakdown
Initiative | Improve First Contact Resolution
Owner | Michael Chen
Description | Implement enhanced knowledge management system and additional support training
Key Activities | 1. Deploy knowledge base platform; 2. Conduct 40-hour training; 3. Implement metrics tracking
Success Metrics | FCR rate 85%+, Customer satisfaction 4.6+
Timeline | 90 days
Budget | $50,000
Expected Impact | 3-point satisfaction increase, 8-point NPS lift